## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Dhiraj Kajale | 2026-01-09 | Model predicts low urgency for emails with unclear but time-sensitive language | Sprint 3 | Dhiraj Kajale | Logic / ML Prediction | Improved training data and adjusted feature extraction | 2026-01-09 | Closed | Prediction accuracy improved
2 | Dhiraj Kajale | 2026-01-10 | Keyword based urgency overrides ML prediction incorrectly in some cases | Sprint 3 | Dhiraj Kajale | Logic | Modified priority rules between keyword and ML prediction | 2026-01-10 | Closed | Inference logic balanced
3 | Dhiraj Kajale | 2026-01-10 | Missing model files during inference execution | Sprint 3 (Model Integration) | Dhiraj Kajale | Configuration | Ensured trained model files were saved and loaded correctly | 2026-01-10 | Closed | Inference working correctly
4 | Dhiraj Kajale | 2026-01-12 | Dashboard failed to load CSV file on Streamlit Cloud | Sprint 4 (Dashboard & Deployment) | Dhiraj Kajale | Deployment | Replaced hardcoded file path with sample dataset and file uploader | 2026-01-12 | Closed | Issue resolved successfully
5 | Dhiraj Kajale | 2026-01-12 | Large CSV file could not be uploaded to GitHub | Sprint 4 (Dashboard & Deployment) | Dhiraj Kajale | Data Management | Created smaller representative sample dataset | 2026-01-12 | Closed | Sample dataset used for dashboard
6 | Dhiraj Kajale | 2026-01-12 | Streamlit app showed FileNotFoundError during deployment | Sprint 4 (Deployment) | Dhiraj Kajale | Runtime Error | Modified dashboard to load sample data by default | 2026-01-12 | Closed | Deployment stable
7 | Dhiraj Kajale | 2026-01-10 | Email stream simulator ran continuously without stopping | Sprint 4 (Testing) | Dhiraj Kajale | Functional | Identified as expected behavior for real time simulation | 2026-01-10 | Closed | No fix required
8 | Dhiraj Kajale | 2026-01-12 | Dashboard performance slow with large dataset | Sprint 4 (Dashboard) | Dhiraj Kajale | Performance | Limited data size using sample dataset | 2026-01-12 | Closed | Performance improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others